## Tracker
Sr No | Task Name | Assigned To (Select Multiple) |  |  | Assigning Date | Deadline Date | Actual Submission
|  | Lead | Support 1 | Support 2
1 | System's Structure , UML & ER Research | Farooq | Farooq | Farooq | 2025-11-27 | 2025-12-04 | 2025-12-04
2 | ER Implementation | Farooq | Abu-Bakar | Dawood | 2025-12-04 | 2025-12-06 | 2025-12-07
3 | UML Implementation | Farooq | Tehami | Umair | 2025-12-04 | 2025-12-06 | 2025-12-07
4 | Basic DB Creation | Farooq | Farooq | Farooq | 2025-12-07 | 2025-12-07 | 2025-12-07
5 | Creating Passenger Class and service class | Farooq | Tehami | Umair | 2025-12-08 | 2025-12-09 | 2025-12-09
6 | Creating Flight Class and service class | Farooq | Dawood | Abu-Bakar | 2025-12-08 | 2025-12-09 | 2025-12-09
7 | Creating Main class | Farooq | Farooq | Farooq | 2025-12-09 | 2025-12-10 | 2025-12-10
8 | Creating DB Connection and data loading classes | Farooq | Farooq | Farooq | 2025-12-09 | 2025-12-10 | 2025-12-10
9 | UML updation(M3) | Farooq | Tehami | Umair | 2025-12-20 | 2025-12-21 | 2025-12-20
10 | ER updation(M3) | Farooq | Farooq | Farooq | 2025-12-20 | 2025-12-20 | 2025-12-20
11 | MILESTONE # 3 IMPLEMENTATION
12 | Linked-List data structure class | Farooq | Farooq | Abu-Bakar | 2025-12-30 | 2026-01-02 | 2026-01-02
13 | Stack data structure class | Farooq | Farooq | Dawood | 2025-12-30 | 2026-01-02 | 2026-01-02
14 | Queue data structure class | Farooq | Farooq | Tehami | 2025-12-30 | 2026-01-02 | 2026-01-02
15 | Hash Table data structure class | Farooq | Farooq | Umair | 2025-12-30 | 2026-01-02 | 2026-01-02
16 | Binary Search Tree | Farooq | Umair | Tehami | 2026-01-05 | 2026-01-08 | 2026-01-08
17 | Custom Fleet Map Data Structure | Farooq | Dawood | Abu-Bakar | 2026-01-05 | 2026-01-08 | 2026-01-08
18 | Admin Conrtoller | Farooq | Umair | Tehami | 2026-01-06 | 2026-01-10 | 2026-01-12
19 | Main Controller | Farooq | Abu-Bakar | Dawood | 2026-01-06 | 2026-01-10 | 2026-01-12
20 | UML classes (System Model) | Farooq | Umair | Tehami | 2026-01-01 | 2026-01-02 | 2026-01-02
21 | Service Logic Classes (Admin , Flight , Passenger) | Farooq | Dawood | Abu-Bakar | 2026-01-10 | 2026-01-13 | 2026-01-13
22 | Service Logic Classes (AirCraft , Booking ) | Farooq | Umair | Tehami | 2026-01-10 | 2026-01-13 | 2026-01-13
23 | Enum Classes | Farooq | Farooq | Farooq | 2025-12-28 | 2025-12-28 | 2025-12-28
24 | Repositary Interfaces | Farooq | Farooq | Farooq | 2025-12-28 | 2025-12-28 | 2025-12-28
25 | Front end UI/UX with spring boot handling | Farooq | Farooq | Farooq | 2025-12-19 | 2026-01-19 | 2026-01-19
Formulas:
Deadline Date = [Assigning Date]+7